## Ownership & Scope
Project | Voice-First Conversational Tutor
Person A | Varshini
Person B | Vaasini
Person A domain | Voice / Realtime
Person B domain | AI / Agent
Domain switch | Primary domains are intentionally switched versus the ISL project.
MVP principle | Build a deterministic, narrow demo before broadening scope.

## Master Tracker
ID | Workstream | Task | Owner | Domain | Priority | Status | Start | Due | Dependency | Acceptance / Done Criteria | Notes
VT-01 | Product | Freeze tutor problem statement and demo lesson | Varshini | Voice / Realtime | P0 | Not started |  |  | None | One agreed 90–120 sec lesson flow
VT-02 | Voice | AssemblyAI realtime audio pipeline | Varshini | Voice / Realtime | P0 | Not started |  |  | VT-01 | Stable partial/final transcript flow
VT-03 | Voice | Turn-taking and interruption | Varshini | Voice / Realtime | P0 | Not started |  |  | VT-02 | Learner can interrupt naturally
VT-04 | Voice | TTS response pipeline | Varshini | Voice / Realtime | P1 | Not started |  |  | VT-02 | Tutor speaks concise responses
VT-05 | AI | Curriculum/problem bank | Vaasini | AI / Agent | P0 | Not started |  |  | VT-01 | At least 10 deterministic problems
VT-06 | AI | Reasoning-state classifier | Vaasini | AI / Agent | P0 | Not started |  |  | VT-02,VT-05 | Correct/partial/misconception/uncertain labels
VT-07 | AI | Tutor strategy policy | Vaasini | AI / Agent | P0 | Not started |  |  | VT-06 | Chooses probe/hint/correction/challenge
VT-08 | AI | Learner state and adaptive difficulty | Vaasini | AI / Agent | P0 | Not started |  |  | VT-07 | Difficulty changes based on performance
VT-09 | Frontend | Voice-first lesson UI | Vaasini | AI / Agent | P0 | Not started |  |  | VT-01 | Minimal topic selection, live state, progress
VT-10 | Integration | End-to-end tutor loop | Varshini | Voice / Realtime | P0 | Not started |  |  | VT-03,VT-07,VT-09 | Problem → explanation → adaptive response works
VT-11 | QA | Latency and interruption tests | Vaasini | AI / Agent | P1 | Not started |  |  | VT-10 | Natural turn-taking in repeated tests
VT-12 | QA | Hallucination/content guardrails | Vaasini | AI / Agent | P1 | Not started |  |  | VT-05,VT-07 | Bounded content remains reliable
VT-13 | Demo | Polish and demo reliability | Varshini | Voice / Realtime | P0 | Not started |  |  | VT-10 | Three consecutive successful runs
VT-14 | Demo | Pitch and architecture visuals | Vaasini | AI / Agent | P0 | Not started |  |  | VT-10 | 90-sec pitch and architecture diagram ready

## Daily Log
Date | Owner | What I did | Blocker | Next action

## Bug Tracker
ID | Project Area | Bug | Owner | Severity | Status | Repro / Notes | Fix

## Demo Checklist
Item | Owner | Status | Pass Criteria
Environment/API keys | Both | Not started | All credentials configured without exposing secrets
Camera/mic permissions | Both | Not started | Permissions work on demo machine
Happy path | Both | Not started | End-to-end run succeeds
Failure path | Both | Not started | Ambiguity produces clarification
Latency | Both | Not started | No distracting stalls
Pitch | Both | Not started | Problem → differentiation → demo → architecture clear

## Roadmap
Horizon | Feature / Capability | Why it matters | Owner | Status | Depends on MVP
Phase 2 | Multi-subject modules | Increase usefulness | Vaasini | Backlog | Yes
Phase 2 | Persistent learner model | Personalize teaching over time | Vaasini | Backlog | Yes
Phase 2 | Multilingual tutoring | Broaden accessibility | Varshini | Backlog | Yes
Phase 2 | Confusion/hesitation signals | Improve adaptive interventions | Varshini | Backlog | Yes
Phase 2 | Proactive revision | Close learning gaps automatically | Vaasini | Backlog | Yes
Phase 3 | Camera homework understanding | Make tutor multimodal | Varshini | Backlog | Yes
Phase 3 | Voice + visual whiteboard | Explain concepts visually | Varshini | Backlog | Yes
Phase 3 | Curriculum planning | Move from single lessons to learning journeys | Vaasini | Backlog | Yes
Phase 3 | Teacher/parent dashboard | Make progress observable | Vaasini | Backlog | Yes
Long-term | Exam/interview/professional modes | Expand addressable market | Vaasini | Backlog | Yes
Long-term | Role-play/debate agents | Practise communication and reasoning | Varshini | Backlog | Yes
Long-term | Low-connectivity lesson packs | Improve access in constrained environments | Varshini | Backlog | Yes
Novelty expansion
Phase 2 — Adaptive tutor | Expand beyond one subject into a small set of verified subject modules. |  |  | Backlog
Phase 2 — Adaptive tutor | Build a persistent learner model covering skill mastery, misconceptions, confidence and preferred teaching style. |  |  | Backlog
Phase 2 — Adaptive tutor | Add multilingual and vernacular tutoring while retaining the same lesson state. |  |  | Backlog
Phase 2 — Adaptive tutor | Detect hesitation, uncertainty and confusion from conversational behavior as supplementary signals. |  |  | Backlog
Phase 2 — Adaptive tutor | Add proactive revision sessions based on demonstrated weaknesses. |  |  | Backlog
Phase 3 — Multimodal learning agent | Add camera input for handwritten work, diagrams, textbook pages and physical demonstrations. |  |  | Backlog
Phase 3 — Multimodal learning agent | Generate visual explanations/whiteboards alongside voice. |  |  | Backlog
Phase 3 — Multimodal learning agent | Allow the learner to switch naturally between voice, text, camera and visual interaction. |  |  | Backlog
Phase 3 — Multimodal learning agent | Add curriculum planning and goal-based lesson sequencing. |  |  | Backlog
Phase 3 — Multimodal learning agent | Add teacher/parent views focused on progress and misconceptions rather than raw transcripts. |  |  | Backlog
Long-term / startup vision | Become a voice-first learning companion that can tutor, challenge, practise and coach rather than simply answer questions. |  |  | Backlog
Long-term / startup vision | Support exam preparation, interview practice, language learning and professional upskilling as separate tutor modes. |  |  | Backlog
Long-term / startup vision | Add peer/debate simulations and role-play agents for communication-heavy learning. |  |  | Backlog
Long-term / startup vision | Support low-connectivity/offline lesson packs for broader access. |  |  | Backlog
Novelty expansion | The strongest differentiator is reasoning-aware tutoring: the agent listens to how a learner thinks, chooses the smallest useful intervention, and adapts the next question instead of simply generating an answer. |  |  | Backlog